## Slide 1: National Certification Committee: Digitization Update
WBENC Board Meeting
November 2015

## Slide 2: Digitization
  Goal
    Integrate digitized business process improvements and technology infrastructure that will eliminate paper, provide operation continuity and stainability while reducing physical file storage within the certification process
  Objectives
    Replace the current paper process for certification application (required documentation)
    Improve the current process for reviewing files (standardization)
    Reduce physical file storage and eliminate paper

## Slide 3: Digitization: Milestones
Deliverable | Notes | Timing
WBENCLink stability assessment | System stabilization is imperative prior to project initiation | January 2013- January 2014 (COMPLETE)
Analysis of certifying entities currently utilizing a digitized process | Government and 3rd party certifiers included in analysis | March 2014 (COMPLETE)
Analysis of required application documentation | Comparison of other certifying entities included in analysis | March 2014 (COMPLETE)
Enhancement and implementation of Recertification process improvements | Six month pilot conducted, post analysis conducted and full implementation completed | October 2013-April 2014 (COMPLETE)
Technology & digitization options discovery (i.e.: best tools, network impact analysis, etc) Tool discovery: Pitney Bowes Tool discovery & network impact: Logistics Solutions | Evaluations and discovery sessions relevant to both approaches; bolt-on and total system conversion | November 2014 (COMPLETE) October 2014-November 2014 (COMPLETE)
Complete initial process mapping for current landscape WBENC mapping RPO Input NCC | Current process consensus amongst WBENC and RPOs is essential to new integration discussions and work | February 2015 (COMPLETE) March 2015 (COMPLETE) March 2015 (COMPLETE)

## Slide 4: Digitization: Milestones
Apply high level process mapping to all RPOs and obtained 6 Hat input from the RPOs relevant to the new system | Provided the WBENC mapping to the RPOs for analysis of each RPO business process to identify gaps & trneds | April 2015 (COMPLETE)
8. Conduct initial RFI | Conducted a search and identified 3 potential suppliers amongst WBENC network firms and 1 Microsoft referral: B2GNow- regional corporate member ConnXus- national corporate member Logistics Solutions, Inc.- MBE firm Prism- WBE firm | April- July 2015 (COMPLETE)
9. Synthesize all RPO mapping and 6 Hat input |  | July 2015 (COMPLETE)
10. Participated in system demo as a result of RFI responses | Of the 4 potential suppliers, demos were conducted by 2: B2GNow ConnXus | July-September 2015 (COMPLETE)
11. Conducted demo of WBENCLink for potential supplier | As a result of the demo’s, WBENC conducted a demo of WBENCLink for one potential supplier: B2GNow | September 2015 (COMPLETE)

## Slide 5: Digitization: Next Steps
Deliverable | Notes | Timing
Document mapping & workflow for transitioning to the new WBENCLink | Evaluation of potential new system and WBENC needs to develop enhanced system & process improvements | October – December 2015
Complete analysis of WBENC WBE application questions to ensure there are no gaps in the data collected during the certification process | Evaluation session is essential to ensuring relevant information is collected for WBENC Standards and sourcing | November - December 2015
3. Selection Process | Selection process will be determined collaboratively and technology impact will be assessed | December 2015
4. Complete comprehensive communication plan |  | October-November 2015
5. Complete implementation plan for transitioning |  | October- December 2015

## Slide 6: THANK YOU!